## Arkusz1
ID | Title | Description | Category | Artist | Status | Notes
#01 | Flashlight attack | Flashlight will have polygon collider which will look for any enemies in range. If enemy detected, will send raycast to enemy to see if there are no objects in way | Programming | Kacper | Done
#02 | Enemy death | If enemy detected and raycast hit after flashlight attack, kill enemy | Programming | Kacper | Done | wysłać maila jak usuwać przeciwników od najbliższego do najdalszego (sortowanie listy po odległości
#03 | Player hp system | Hp for player, conditions for lose and gain | Programming | Kacper | Done
#04 | Player taking damage | If player contacts with enemy, knock back player and take damage (-1hp), stop enemy from moving to allow player escape | Programming | Kacper | Done | enemy does not stop from moving
#05 | Attack cooldown | Add cooldown for flashlight attacks | Programming | Kacper | To do
#06 | Basic tilemap | Create basic tilemap (those 12 tiles) | Graphics | Julka | In progress
#07 | Add tilemap to Unity | Import tilemaps to unity and make them work | Setup | Julka | In progress
#08 | Add shadows for tilemap | Add script for auto shadow cast 2d for tilemap (ask Dawid for script) | Setup | Kacper | To do
#09 | Menu | Add simple main menu and basic logic | Setup | Kacper | To do
To do
In progress
Done
Kacper
Julka